# Project Planning Phase

A Sprint is a fixed period or duration in which a team works to complete a set of tasks.

An Epic is a big task or project that is too large to complete in one sprint. It is broken down into smaller tasks (stories) that can be completed over multiple sprints.

A Story is a small task. It is part of an Epic.

A Story Point is a number that represents how much effort a story takes to complete (usually in the form of Fibonacci series).

Very Easy task

Normal task

Moderate task

Difficult task

Storypoint -5 (1,2,3,5)

## Sprint 1

User Management (Epic 1)

User Registration (USN1) 2

User Login (USN2) 2

Course Management (Epic 2)

Create Course (USN3) 3

Update/Delete Course (USN4) 3

Authentication (Epic 3)

JWT Implementation (USN5) 3

Total Story Point in Sprint 1 = 2+2+3+3+3 = 13

## Sprint 2

Course Enrollment (Epic 4)

Enroll in Course (USN6) 3

View Enrolled Courses (USN7) 2

Learning Module (Epic 5)

Video Player Integration (USN8) 3

Progress Tracking (USN9) 3

Certificate Module (Epic 6)

Certificate Generation using PDFKit (USN10) 5

Total Story Point in Sprint 2 = 3+2+3+3+5 = 16

## Total Story Points

Sprint 1 = 13

Sprint 2 = 16

Velocity = Total Story Points Completed / Number of Sprints

Total Story Points = 13 + 16 = 29

Number of Sprints = 2

Velocity = 29 / 2

14.5 (≈ 15 Story Points per Sprint)

Your team’s velocity is approximately 15 Story Points per Sprint.